## Gantt planification
Content Marketing Plan
Teresa
2019-09-06 16:30
|  | September 2019 | October 2019 | [22 empty] | November 2019 | [20 empty] | December 2019 | [21 empty] | January 2020
 | time axis 2019-09-30 to 2020-01-03
Project activities | Status | time axis 2019-09-30 to 2020-01-03
Market Research | todo | bar: 2019-10-01 to 2019-10-07
Meeting - Presentation | todo
Meeting - Design KPIs | todo | bar: 2019-10-04 to 2019-10-10
Analysis of Direct Competition | todo
Meeting - Target | todo | bar: 2019-10-15 to 2019-10-16
Design Objetives | todo
Design Content | todo | bar: 2019-10-23 to 2019-10-29
Design Channels | todo
PR Strategy | todo | bar: 2019-10-23 to 2019-10-29
Webinars | todo
Design Social Strategy | todo | bar: 2019-11-07 to 2019-11-13
Ebook | todo
Meeting 2 | todo | bar: 2019-11-14 to 2019-11-18
Content | todo
Social Media automations | todo | bar: 2019-12-09 to 2019-12-13
Email MK automations | todo
Analytics | todo

## Project overview
Content Marketing Plan
Teresa
2019-09-06 16:30
Project team | Role
Teresa Canive | Project owner
Jonas Jonas | Team member
Activity | Involved | Goals | Subtasks | Assigned to | Date | Time
Market Research
1 Oct 2019 - 7 Oct 2019 (5 days) |  | No goals | No subtasks
Meeting - Presentation
1 Oct 2019 - 3 Oct 2019 (3 days) |  | No goals | No subtasks
Meeting - Design KPIs
4 Oct 2019 - 10 Oct 2019 (5 days) |  | No goals | No subtasks
Analysis of Direct Competition
8 Oct 2019 - 14 Oct 2019 (5 days) |  | No goals | No subtasks
Meeting - Target
15 Oct 2019 - 16 Oct 2019 (2 days) |  | No goals | No subtasks
Design Objetives
17 Oct 2019 - 22 Oct 2019 (4 days) |  | No goals | No subtasks
Design Content
23 Oct 2019 - 29 Oct 2019 (5 days) |  | No goals | No subtasks
Design Channels
23 Oct 2019 - 29 Oct 2019 (5 days) |  | No goals | No subtasks
PR Strategy
23 Oct 2019 - 29 Oct 2019 (5 days) |  | No goals | No subtasks
Webinars
30 Oct 2019 - 6 Nov 2019 (6 days) |  | No goals | No subtasks
Design Social Strategy
7 Nov 2019 - 13 Nov 2019 (5 days) |  | No goals | No subtasks
Ebook
7 Nov 2019 - 26 Nov 2019 (14 days) |  | No goals | No subtasks
Meeting 2
14 Nov 2019 - 18 Nov 2019 (3 days) |  | No goals | No subtasks
Content
19 Nov 2019 - 6 Dec 2019 (14 days) |  | No goals | No subtasks
Social Media automations
9 Dec 2019 - 13 Dec 2019 (5 days) |  | No goals | No subtasks
Email MK automations
9 Dec 2019 - 13 Dec 2019 (5 days) |  | No goals | No subtasks
Analytics
16 Dec 2019 - 20 Dec 2019 (5 days) |  | No goals | No subtasks